## Sheet1
# | Task | Duration (Days) | Due Date | Complete | Notes
A. Building the Software
1 | Start | 0 | 2019-06-20
1 | Capturing of data System | 3 | 2019-06-22 | 66.67% | Designed a manual input UI
2 | monitor the growth process of flower farm | 4 | 2019-06-24 | 0%
3 | give insights | 3 | 2019-06-27 | 0%
4 | Reporting System | 4 | 2019-07-01 | 0%
5 | AI integration to give predictions and patterns | 7 | 2019-07-08 | 0%
6 | Improve UI/UX | 3 | 2019-07-11 | 0%
7 | Debug | 6 | 2019-07-17 | 0%
| Total Duration | 30 | 2019-08-16 | 6.667%
B. Build IoT Devices
C: Integrating Software and Devices
Formulas:
Complete = IF(((TODAY()-[Due Date, row above])/[Duration (Days)])>=0,(TODAY()-[Due Date, row above])/[Duration (Days)],0)
Complete = IF(((TODAY()-D3)/[Duration (Days)])>=0,(TODAY()-D3)/[Duration (Days)],0)
Due Date = D3+[Duration (Days)]
Due Date = [Due Date, row above]+[Duration (Days)]